The Bible Church Campaign Planning Template

Use this template to plan The Bible Church Campaign, group study, or outreach programs. Add or delete rows as necessary and fill in the template with the names of the owners and due dates for each activity. The template has some suggested timeframes and actions; you can replace these with your own.

| Action/Deliverable | Owner | Date | Comments/Status |
| --- | --- | --- | --- |
| Leadership and Vision |  |  |  |
| Conduct initial planning meeting with the church board or elders. | Senior Pastor/ Outreach Team | 6+ weeks out | Use materials from this Church Kit such as The Bible promotional trailer on the Resources DVD/CD to help you cast a vision. |
| Hold vision meeting with the lay leaders of the church. | Senior Pastor | 5+ weeks out |  |
| Church leadership and prayer team begin praying for campaign. |  | 5+ weeks out |  |
| Sermons and Services |  |  |  |
| Sermons |  |  |  |
| Review the five Bible sermons. | Senior Pastor | 3-4 weeks out | Determine how many sermons to use and how to customize them. |
| Customize The Bible sermons. | Senior Pastor | Before service | Tailor the messages to the needs of the congregation and your personal style. |
| Videos, Drama, and Music |  |  |  |
| Select appropriate music, drama, testimonials, | Worship Leader | 1-3 weeks before services | See The Bible Resources DVD for videos and power point templates |
| In-Reach Promotion |  |  |  |
| Interior Banners and Posters |  |  |  |
| Order The Bible banners and posters. |  | 6 weeks out | Visit bibleseriesoutreach.com or call 800-991-6011. |
| Begin displaying interior banners and posters. |  | 3-4 weeks out | Display these in the lobby, sanctuary, hallways, and other high-traffic areas. |
| Bulletins |  |  |  |
| Order The Bible Bulletin Guides or bulletin shells. |  | 4 weeks out | You can choose to use the eight-page Bulletin Guides in place of your regular bulletin shells or in conjunction with your regular shells. See the Resource Guide for more information on Bulletin Guides. |
| Announcements |  |  |  |
| Prepare bulletin insert for sign-ups for small groups. |  | 4 weeks out | See bulletin insert included on The Bible Resource DVD/CD. |
| Play The Bible in-reach promotional trailer during your weekend service(s) and announce the start date for the follow-up series. |  | 3-4 weeks out | The promotional video is on The Bible Resource DVD/CD. |

| Action/Deliverable | Owner | Date | Comments/Status |
| --- | --- | --- | --- |
| Outreach Promotion |  |  |  |
| Website, Social Media and PR |  |  |  |
| Review the Digital Marketing tips |  | 6 weeks out |  |
| Create a social media strategy. |  | 5 weeks out |  |
| Update the church website with web graphics and promotional videos. |  | 4 weeks out | Use The Bible graphics and videos on the DVD/CD. |
| Direct-Mail |  |  |  |
| Establish direct-mail budget. |  | 6 weeks out | Call Outreach at 800-991-6011 to talk with an Outreach Specialist. The Specialist can help you select your target direct-mail area, determine the number of cards to send, and establish your budget. |
| Select your direct-mail postcard design, target mailing area, and desired number of recipients. |  | 6 weeks before first service | See above. |
| Order The Bible direct-mail postcards. |  | 4 weeks before first service | See above. |
| Mail The Bible postcards. |  | 2 weeks before service | You can mail your own cards or have Outreach mail them for you. |
| Outdoor Banners |  |  |  |
| Order The Bible outdoor banner(s). |  | 5 weeks before | Contact Outreach at Outreach.com or 800-991-6011. |
| Display The Bible banner(s) outside the church. |  | 2-3 weeks before | The banner(s) will inform and invite your community to The Bible services. |
| Door Hangers |  |  |  |
| Order The Bible door hangers. |  | 3 weeks before | Contact Outreach at Outreach.com or 800-991-6011. |
| Recruit volunteers to distribute door hangers. |  | 3 weeks out | Select leaders and establish teams. |
| Select target communities and print maps for door hanger teams. |  | 3 weeks out | Assign areas to teams and indicate on each map. |
| Distribute The Bible door hangers in your community. |  | Within 1 week of event | Use door hangers to invite your neighbors to The Bible events. |
| Personal Invitations |  |  |  |
| Order The Bible mailers, invite cards or viewing party kits and make them available to your members. |  | 4 weeks out | Visit bibleseriesoutreach.com or call 800-991-6011. These tools will equip your members to invite their friends, family, co-workers, and neighbors to The Bible services and viewing parties. |

| Action/Deliverable | Owner | Date | Comments/Status |
| --- | --- | --- | --- |
| Follow-Up Campaign Planning |  |  |  |
| If you are a planning a follow-up campaign, begin reviewing those materials and start your planning. | Senior Pastor | 4-6 weeks before | To keep visitors coming back, launch The Bible small groups |
| Pray for the small group study program and small group leaders. |  | 4 weeks out |  |
| Recruit new leaders, if necessary. |  | 2 weeks before | Contact possible leaders by e-mail and phone. |
| Hold small group kickoff meeting and training. |  | 2-3 weeks before first group meeting | Review basic techniques for small group leadership. |
| Small Group Materials |  |  |  |
| Confirm number of small groups. |  | After kickoff |  |
| Estimate number of participants and order study guides or materials for each participant. |  | 3-5 weeks before first meeting | Include those already attending groups and anticipated new participants invited by leaders and the church’s in-reach campaign. |
| Begin distributing small group materials. |  | On arrival of material | Sell or provide free of charge, based on church budget. Distribute through leaders or at a central location. |
| Small Group Promotion and Participants |  |  |  |
| Prepare bulletin insert for sign-ups. |  | 5 weeks out | See bulletin insert included on The Bible Resource DVD/CD. |
| Begin using bulletin insert for sign-ups. |  | 3-4 weeks out |  |
| Include The Bible follow-up campaign small group announcements in bulletin. |  | 3-4 weeks out | Do pulpit announcements. |
| Provide additional sign-up sheets at a central location, such as a lobby or information center. |  | 3-4 weeks out |  |
| Send an e-mail to church e-mail list encouraging small group participation. |  | 3 weeks out |  |
| Distribute first list of small group participants to leaders. |  | 3 weeks out |  |
| Leaders begin calling group participants. |  | 2-3 weeks out | Leaders should confirm membership in their group and provide directions and the time/date for the first group meeting. |
| Complete final sign-ups and announcements. |  | Sunday before first group meeting |  |
| Distribute final member lists to leaders. |  | Week of first group meeting |  |